## Sheet1
Requirements Traceability Matrix
Project Name: |  | OrangeHRM |  | Document Author: |  | QA Team
Requirement ID | Requirement Name / Description | Requested / Approved By: | Scope Deliverable or Feature | Scope ID | User Story or Work Package | Assigned To | Test Case | Current Staus | Bug ID
Req - 01 | HR Admin Account Login | Product Owner | Login | Scope - 1 | As an HR Admin, I want to log in to access administrative functions | Ahmed Abdallatif | TC - 001 to TC - 026 | Failed | Bug - 01 / Bug - 02
Req - 2 | Admin creates/edits/deletes users | Product Owner | Admin > User Management > Users | Scope - 2 | As an HR Admin, I want to manage user accounts with roles and statuses | Ahmed Abdallatif | TC - 027 to TC - 097 | Failed | Bug - 03 / Bug - 04
Req - 3.1 | Admin defines job titles | Product Owner | Admin > Job > Job Titles | Scope - 3.1 | As an HR Admin, I want to create validated job titles | Mohammad Badawi | TC - 098 to TC - 107 | Failed | Bug - 05 / Bug - 06
Req - 3.2 | Admin defines pay grades | Product Owner | Admin > Job > Pay Grades | Scope - 3.2 | As an HR Admin, I want to set logical salary ranges | Mohammad Badawi | TC - 108 to TC - 117 | Failed | Bug - 07
Req - 3.3 | Admin manages employment statuses | Product Owner | Admin > Job > Employment Status | Scope - 3.3 | As an HR Admin, I want to track employee statuses | Mohammad Badawi | TC - 118 to TC - 125 | Failed | Bug - 08 / Bug - 09
Req - 3.4 | Admin defines job categories | Product Owner | Admin > Job > Job Categories | Scope - 3.4 | As an HR Admin, I want to categorize jobs with naming rules | Mohammad Badawi | TC - 126 to TC - 134 | Failed | Bug - 10 / Bug - 11
Req - 3.5 | Admin manages work shifts | Product Owner | Admin > Job > Work Shifts | Scope - 3.5 | As an HR Admin, I want to assign employees to shifts | Mohammad Badawi | TC - 135 to TC - 144 | Passed | ____
Req - 4.1 | Admin edits company info (name, tax ID) | Product Owner | Admin > Organization > General Information | Scope - 4.1 | As an HR Admin, I want to update company details | Wajiha Al-Amassi | TC - 145 to TC - 160 | Failed | Bug - 12 / Bug - 13 / Bug - 14
Req - 4.2 | Admin adds/manages locations | Product Owner | Admin > Organization > Locations | Scope - 4.2 | As an HR Admin, I want to track office locations | Wajiha Al-Amassi | TC - 161 to TC - 184 | Passed | ____
Req - 5.1 | Admin defines skills | Product Owner | Admin > Qualifications > Skills | Scope - 5.1 | As an HR Admin, I want to standardize employee skills | Nagham Taweel | TC - 185 to TC - 194 | Passed | ____
Req - 5.2 | Admin manages education levels | Product Owner | Admin > Qualifications > Education | Scope - 5.2 | As an HR Admin, I want to list accepted education levels | Nagham Taweel | TC - 195 to TC - 199 | Passed | ____
Req - 5.3 | Admin defines languages | Product Owner | Admin > Qualifications > Languages | Scope - 5.3 | As an HR Admin, I want to list company languages with validation | Nagham Taweel | TC - 200 to TC - 204 | Passed | ____
Assigned To
Ahmed Abdallatif
Nagham Taweel
Wajiha Al-Amassi
Mohammad Badawi
Current Staus
Passed
Failed